SCOPE COMPARISON

Proposal vs. Business Requirements Document

Redwave Sales & Commission Platform — Phase 2

Prepared by  Fathom (Development Partner)

Prepared for  Redwave Marketing Inc.

Documents compared  Phase 2 Proposal (3 May 2026)  vs.  BRD v1.2 — Baseline (approved for build)

Date  2 June 2026

# Purpose of this document

The Phase 2 Proposal was an early estimate built on the assumption that we would repair and extend the existing Phase 1 platform. Since then, two working sessions and a revised commission schedule (Schedule C v2) produced a consolidated baseline: the Business Requirements Document, version 1.2.

The BRD is a stronger, clearer specification — and we are glad to be building from it. Several decisions reached together during that process, however, changed both the nature and the size of the work. This document sets the two artifacts side by side so the scope difference is transparent, and so any revision to pricing is grounded in agreed facts rather than surprise.

The single most important change The Proposal priced a series of fixes and additions on top of Phase 1. The BRD specifies a clean-slate build — “no code, schema, or frontend from any prior system is reused.” This re-bases most of the Phase 2 estimate: items originally quoted as fixes or verifications against existing code are now full builds. It is the primary driver behind a revised quotation.

Each item below is tagged with its direction of impact. We have deliberately included the items that reduce or remove scope as well, so the net picture is fair.

# A.  New scope introduced by the BRD

These items are present in the BRD but were not part of the Proposal’s priced scope.

| Area | What the Proposal assumed | What the BRD v1.2 requires | Pricing impact |
| --- | --- | --- | --- |
| Build approach | Fixes, logic rebuilds, and new features layered on the existing Phase 1 platform. | Clean-slate rebuild; nothing from any prior system is reused. | Significant increase |
| Market coverage | Manitoba, Canada only. | Canada plus select US markets (CTI is the US program). Sale ID and matching logic is built around this. | Increase |
| Payroll export | Pay-run rebuild, but no external payroll-system output. | ADP-ready, configurable export module designed from scratch. | Increase |
| AI chatbot | M3 “Could Have” — keep and update the existing chatbot. | In-scope, integrated Gemini-powered assistant grounded on Redwave’s data, with role-based access. | Increase |
| Sale ID system | Not specified. | Composite unique Sale ID (date + MPU ID + client), duplicate-address handling, and MPU-based report matching. | Increase |
| Mobile readiness | Mobile app deferred to Phase 3; out of scope. | Versioned, API-first architecture to be built now so a future mobile app can share the backend. | Increase |
| Expense categories | Kilometres, meals, and an “other” field. | Adds Hotel, Flight, Rental, and Gas Money as structured categories, plus admin-configurable expense fields. | Moderate increase |
| Parallel-run cutover | Not specified. | 1–2 pay cycles run alongside the manual process before full cutover. | Increase |

# B.  Items that grew in complexity

These were present in the Proposal in some form but are specified more demandingly in the BRD.

| Area | What the Proposal assumed | What the BRD v1.2 requires | Pricing impact |
| --- | --- | --- | --- |
| Configuration model | Business values described as “configurable.” | Effective-dated configuration across all values; changes are prospective only and never rewrite closed periods. | Increase |
| Holdback release | Fixed rule — 30% releases on the 3rd cycle (~45 days). | Super-Admin-set release cycle (bulk, sticky) plus a Holdback Ledger tracking each hold and its release. | Increase |
| Data integrity | General expectation of correctness. | Immutable per-sale snapshots; every paid figure must be reconstructable for accurate clawback. | Increase |
| Roles & hierarchy | Five roles (Super Admin, Manager, Rep, Finance, Custom). | New Admin role and a mandatory Field-Manager assignment for every rep. | Minor increase |
| Commission tally | Tiered commission rewrite. | Gross, cross-client tally aggregation rule specified explicitly. | Confirm in estimate |

# C.  Items that reduce or remove scope

In fairness, the BRD also simplifies or drops several things from the Proposal. These offset part of the increases above.

| Area | What the Proposal assumed | What the BRD v1.2 requires | Pricing impact |
| --- | --- | --- | --- |
| Clawback logic | 30/60-day windows, tier-cascade re-tiering, and 70/30 sequencing. | Flat dollar-for-dollar deduction; no in-system date math or sequencing. | Reduction |
| M3 “Could Have” items | DocuSign-style signing, 2FA, partial clawback, cohort ramp tracking, landing-page rebuild. | Not in the BRD scope. | Reduction |
| Invoice tax | GST/PST included on statements/invoices. | Removed entirely; handled in QuickBooks. | Minor reduction |
| Commission values | Tier thresholds and rates as in Schedule C v1. | Schedule C v2 values (thresholds, rates, greenfield $100, home phone $30). Configurable, not new engineering. | Confirm in estimate |

# What this means for pricing

The original Proposal figures were tied to a fix-and-extend approach. With the BRD now confirming a clean-slate build plus the new scope above, those figures no longer reflect the agreed work. The reductions in Section C are real but do not fully offset the move to a ground-up build.

We propose to re-baseline the quotation directly against the BRD, keeping the same phased (M1 / M2 / M3) and payment structure already agreed. Concretely:

- Re-estimate each milestone against the BRD as the single source of truth, mapped item-by-item to the changes in this document.

- Issue a revised Phase 2 quotation reflecting the clean-slate build, the new scope items, and the offsetting reductions.

- Confirm the open items the BRD itself flags — the ADP export schema and CTI’s product catalogue — so nothing is left ambiguous before build.

Our intent is simply to make sure the price matches the platform the BRD describes. We’re happy to walk through any line in this comparison together.